## Project Plan
Task ID | Workstream | Task name | Description | Task owner | Client / location | Status | Priority | Start date | End date | Duration (working days) | Completion % | Budget (£) | Actual cost (£) | Variance (£) | Dependency ID | Risk / notes | Auto status | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30
T01 | Initiation | Project initiation | Kick-off meeting, project charter and governance setup | Oliver Bennett | London | Complete | High | 2026-01-05 | 2026-01-09 |  | 100% | 2500 | 2450 |  | - | Charter signed off by sponsor
T02 | Discovery | Requirements gathering | Stakeholder workshops and requirements catalogue | Amelia Clarke | Manchester | Complete | High | 2026-01-08 | 2026-01-16 |  | 100% | 4200 | 4380 |  | T01 | Requirements sign-off obtained
T03 | Design | Solution design | High-level and detailed solution design documents | Harry Wilson | Birmingham | In progress | High | 2026-01-15 | 2026-01-26 |  | 90% | 6750 | 6100 |  | T02 | Design authority review pending
T04 | Data | Data migration planning | Data cleansing strategy and migration rehearsal plan | Sophie Taylor | Leeds | Complete | Medium | 2026-01-22 | 2026-02-02 |  | 100% | 5100 | 5025 |  | T02 | Legacy data quality issues flagged
T05 | Procurement | Supplier onboarding | Supplier due diligence, contracts and purchase orders | Jack Evans | Bristol | In progress | Medium | 2026-01-29 | 2026-02-09 |  | 75% | 3850 | 3900 |  | T01 | Awaiting supplier insurance documents
T06 | Build | System configuration | Core system build, workflows and integrations | Emily Thomas | Glasgow | In progress | High | 2026-02-05 | 2026-02-20 |  | 50% | 9500 | 5200 |  | T03 | Integration environment access delayed
T07 | Testing | User acceptance testing | UAT script execution and defect triage | George Roberts | Liverpool | In progress | High | 2026-02-19 | 2026-03-02 |  | 30% | 7250 | 2400 |  | T06 | Defect fix capacity constrained
T08 | Training | Staff training | Training materials, sessions and floorwalking support | Isla Walker | Sheffield | Not started | Medium | 2026-02-26 | 2026-03-06 |  | 10% | 4600 | 600 |  | T06 | Trainer availability confirmed
T09 | Deployment | Go-live and handover | Cutover, hypercare and handover to business as usual | Charlie Hughes | Edinburgh | Not started | High | 2026-03-09 | 2026-03-13 |  | 0% | 3900 | 0 |  | T07, T08 | Go-live criteria agreed with sponsor
Project totals |  |  |  |  | Completed tasks:

## Dashboard
Project Dashboard — Management Summary
Project information
Project name | Orion ERP Implementation
Client | Northgate Retail Group
Project manager | Oliver Bennett
Reporting date
Currency | GBP (£)
Key performance indicators
Total project budget | Actual spend | Cost variance | Average completion | Completed tasks | Overdue tasks
[6 empty] | Status | Tasks
Budget position: | [5 empty] | Not started
In progress
Task spotlight | [5 empty] | Complete
Enter Task ID (T01–T09): | T06 |  |  |  |  | On hold
Task name
Task owner
Status (recorded) | [5 empty] | Workstream | Budget (£) | Actual (£)
Auto status | [5 empty] | Initiation
Budget | [5 empty] | Discovery
Completion | [5 empty] | Design
Cost variance | [5 empty] | Data
Procurement
Build
Gantt colour legend | [5 empty] | Testing
| Complete |  |  |  |  | Training
| In progress |  |  |  |  | Deployment
Overdue
Not started
| Milestone (single-day task) |  |  |  |  | Task owner | Completion %
Oliver Bennett
Amelia Clarke
Harry Wilson
Sophie Taylor
Jack Evans
Emily Thomas
George Roberts
Isla Walker
Charlie Hughes

## Instructions
Instructions — UK Project Gantt Chart Template
How to use this workbook
• Yellow cells are for user input; all other cells contain formulas or calculated values.
• Enter dates in DD/MM/YYYY format (for example 05/01/2026).
• Update Status, Completion %, Budget and Actual cost regularly so that reporting stays accurate.
• The Gantt bars update automatically from each task's Start date and End date.
• Use the Dashboard sheet for management reporting and project board packs.
• Review VAT, supplier costs and project expenditure in line with your organisation's normal bookkeeping and HMRC record-keeping procedures.
• Do not overwrite formula cells (Duration, Variance, Auto status, totals and the timeline area).
Sheet guide
• Project Plan — the main working sheet. Enter one row per task, choose Status and Priority from the dropdown lists, and view the weekly Gantt timeline from 05/01/2026 to 30/03/2026.
• Dashboard — KPI cards, task spotlight lookup, Gantt colour legend and charts for management reporting.
• Instructions — this guidance sheet.
Gantt colours
• Navy = complete task • Teal = in progress • Red = overdue • Grey = not started • Dark red = milestone (single-day task).
Key formulas
• Duration uses NETWORKDAYS, counting working days only (Monday to Friday).
• Variance is Budget minus Actual cost; a negative (red) figure means the task is over budget.
• Auto status compares today's date with the task dates and the recorded completion percentage.